## sheet 1
RISK ANALYSIS TABLE for HomeHaven
Last Update:
Ranking | Threats (1) | Vulnerabilities (2) | Contextual factors | Risks (3) | Likelihood from 1 to 5 | Impact from 1 to 5 | Reduction of Threats (Acceptance Strategy) | Reduction of Vulnerabilities (Protection Strategy) | Level of residual Risk
20 - Critical | Unauthorized access, data breaches, or privacy violations | Weak encryption, inadequate access controls, insufficient user authentication | Handling sensitive user information, compliance with data protection regulations | User Data Security and Privacy | 4 | 5 | Implement incident response plans and communication strategies to mitigate the impact if a data breach occurs | Encrypt sensitive user data both at rest and in transit, implement multi-factor authentication for user accounts, conduct regular security audits and penetration testing, and ensure compliance with relevant data protection regulations (e.g., GDPR, CCPA) | 8 - Medium
12 - High | Mishandling of registration keys leading to unauthorized access or confusion in user profiles | Insecure key generation, improper key distribution, lack of key validation | Importance of user authentication, reliance on registration keys for user access | Registration Key Handling | 3 | 4 | Mitigate this by implementing thorough key generation, distribution, and validation processes. Have a protocol for handling key-related incidents | Use strong encryption algorithms for key generation and storage, implement secure key distribution channels, regularly audit key usage and revoke inactive or compromised keys, and educate users on the importance of keeping their keys secure | 6 - Low
12 - High | System downtime or glitches impacting user experience and satisfaction | Software bugs, hardware failures, inadequate system monitoring | Dependence on system availability for user operations, reputation management | System Reliability | 3 | 4 | Develop a robust incident response plan to minimize downtime and mitigate the impact on users | Implement redundancy and failover mechanisms to minimize downtime, regularly monitor system performance and conduct proactive maintenance, implement automated alerts for system anomalies, and have a dedicated support team for prompt issue resolution | 6 - Low
8 - Medium | Errors in financial calculations leading to inaccurate fee calculations or financial reports | Flaws in calculation algorithms, data entry errors, lack of validation checks | Financial transparency, legal compliance with financial reporting requirements | Financial System Accuracy | 2 | 4 | Implement regular audits and reconciliation processes to identify and correct inaccuracies promptly | Use reliable financial calculation algorithms, implement validation checks for data entry, conduct regular audits of financial transactions, and provide transparency to users by allowing them to review their financial statements | 3 - Very low
9 - Medium | Unauthorized access or loss of condo files compromising privacy or legal compliance | Weak file encryption, inadequate access controls, lack of versioning and auditing | Legal obligations for file retention and privacy, importance of document integrity | File Security and Accessibility | 3 | 3 | Implement encryption, access controls, and regular backups to minimize the impact of potential breaches | Encrypt stored files, implement access controls based on user roles, maintain audit logs for file access, conduct regular backups with off-site storage, and implement versioning to track changes and revisions | 4 - Low
6 - Low | System glitches or manipulations leading to reservation conflicts or mismanagement | Software bugs, improper validation of reservations, lack of conflict resolution mechanisms | Dependence on system for facility management, user satisfaction with reservation process | Reservation System Integrity | 2 | 3 | Implement clear communication channels and a manual fallback process in case of system failures | Thoroughly test the reservation system for reliability and scalability, implement automated conflict resolution mechanisms, regularly update and maintain the system, and provide user support for assistance with reservations | 2 - Very low
9 - Medium | Improper role assignments leading to security vulnerabilities or mismanagement | Inadequate role-based access controls, lack of regular role audits, weak authentication mechanisms | Employee responsibilities, segregation of duties, compliance with regulatory requirements | Employee Roles and Permissions | 3 | 3 | Implement regular audits and training programs to ensure compliance with role-based access controls | Implement a robust role-based access control system, conduct regular audits of employee roles and permissions, provide training on role responsibilities and security best practices, and enforce the principle of least privilege | 4 - Low
5 - Low | Failure in assigning requests or notifications leading to delays in issue resolution or communication breakdown | Inefficient request tracking system, lack of automation for notifications, unclear assignment processes | Timely issue resolution, user satisfaction with communication channels | Request Management and Notification System | 2 | 3 | Implement clear communication channels and escalation procedures to address any delays promptly. | Implement an efficient request tracking system with automated notifications, ensure clear assignment processes and escalation paths for unresolved issues, and provide regular training for employees on request management procedures | 2 - Very low
12 - High | Inappropriate content or misuse of forum/events features may harm community relations | Technical vulnerabilities such as software bugs or platform instability. Management vulnerabilities such as ineffective moderation or inadequate event planning. | Importance of user engagement and community building within the forum. Impact of successful event management on user satisfaction and retention. | Forum and Event Management | 3 | 4 | Establish clear communication channels for users to report issues and provide feedback, and develop contingency plans for handling unexpected disruptions during events. | Implement regular testing and monitoring of the forum and event management systems to identify and address technical vulnerabilities proactively. Train moderators on effective community management and event planning techniques, and establish clear guidelines and protocols for organizing and moderating forums and events. Additionally, maintain open communication with users to gather feedback and address concerns promptly. | 6 - Low
6 - Low | Mismanagement of discounts/offers may lead to legal or financial issues | Management vulnerabilities such as miscommunication or mismanagement of discount terms. External vulnerabilities such as reliance on third-party vendors for offers. | Impact of discounts and offers on user satisfaction and retention. Legal and financial implications of mismanaged promotions | Discounts and Offers | 2 | 3 | Establish a process for reviewing and approving discount terms and offers to minimize misunderstandings, and develop a protocol for handling customer complaints or disputes related to promotions. | Implement clear and transparent communication channels for promoting discounts and offers, ensuring that terms and conditions are easily accessible to users. Regularly review and update discount policies and procedures to address changing business needs and regulatory requirements. Additionally, maintain open communication with third-party vendors to ensure alignment on promotion terms and resolve any issues promptly. | 2 - Very low
CONFIDENTIAL